## Sheet1
DATE | WORK | DOING | DONE | WILL DO
2018-03-23 | starting with html page | learning basic html5 with css3 | learnt basic structure for website | Home page
2018-03-24 | navigation bar | navigation bar using html and css | header is ready with design | Main section
2018-03-25 | Sunday |  |  | Main section
2018-03-26 | main content | common structure for main content | common design for title, subtitle and paragraph | about us section
2018-03-27 | about us content design | about us page with bootstrap classes | combine bootstrap with html page | service section
2018-03-28 | services content design | add font awesome into library | add some icons and done services section | log in section
2018-03-29 | log in page | log in form and registration form | done both forms with design | contact us section
2018-03-30 | contact us page | message/ appointment form | details of developer with contact form | feedback section
2018-03-31 | Sunday |  |  | feedback section
2018-04-01 | feedback page | feedback form | feedback section with form | footer
2018-04-02 | footer, page layout | footer design | website layout with minimum requirements | template design
2018-04-03 | final touch to design | add bootsttrap class to fix header and footer | improvise design with content | documentation
2018-04-04 | documentation | Introduction | introduction
2018-04-05 |  | wireframe | wireframe, site map
2018-04-06 |  | design | design,font, color
2018-04-07 |  | form section - wireframe | documentation for website design | responsive web services
2018-04-08 | google map | google map | design structure documentation | weather widget
2018-04-09 | weather tricker | weather widget | google map | social news feed
2018-04-10 | combine webservices | social news feed implementation | social side bar in feedback section | database design
2018-04-11 | database design | database design | manual data table | database implementation
2018-04-12 | complete assesment | database implementation in my sql | design with documentation | Done everything